## Website update list
NEMI website: everything to update before the S-4
Live site nemilmm.com read page by page on 28 Sep 2026, 15 pages, 47 images, 14 videos, checked against the website plan of 18 Sep 2026 and the vShare investor deck of Aug 2026. 44 items. Fill the two cream columns.
# | Page | Where | What is there now | Type | Risk | Why it matters | What to do | Owner | Status | Evidence / decision | Counsel sign-off
1 | About | CEO bio | Built NEMI greenfield to 300k sq ft | Corporate history | High | Contradicts the letter and the deck: the MaaS business was acquired | Rewritten on the branch as acquired and expanded | CFO | Fixed on branch
2 | About | Leadership | Kevin Flick added as CFO, Gokul Madhavan to CSO | Officer change | High | Live site still shows the old structure; the deck shows the old CFO too | Push the branch, and fix the deck | CEO | Fixed on branch
3 | About | Advisory bench | Vinod Dasari, Ramesh Mangaleswaran, Sampath Ravinarayanan, Naoya Nishimura, Sam Swaminathan | Biographical | High | Titles and roles differ from the deck; the S-4 lists directors exactly, and family relationships must be disclosed | Confirm each seat, title and any family relationship | CEO + counsel | Not fixed | Adviosrs should be added
4 | About, Master Plan | Letter | Absolutes and the cellphone prediction, no FLS note | Disclosure | High | De-SPACs have no safe harbour for forward-looking statements | Softened and FLS note added on the branch | Counsel | Reverted on branch | 5 Oct: Master Plan page restored to the live wording on request, so the letter carries this again. About keeps the softened text.
5 | About, Master Plan | Letter | MaaS is profitable on its own, throws off real cash | Financial | High | Same profitability problem as the home page | Softened on the branch | CFO | Reverted on branch | 5 Oct: Master Plan page restored to the live wording on request, so the letter carries this again. About keeps the softened text.
6 | All pages | Site-wide | No forward-looking statements page, no legends page | Disclosure | High | Nothing on the site carries the legends the transaction will require | Legends page drafted, unpublished | Counsel | Drafted | Not Needed
7 | Blog | New post | The World Order post, five historical photographs | Licensing | High | None of the five is licensed to NEMI. One carries a Bayer AG credit, one looks like agency photojournalism | Licence or replace with public-domain sources | Marketing | Drafted | not a problem
8 | Case Drone | Client block | Bengaluru, founded 1997, CEMILAC, partner to leading agencies | Customer identity | High | Identifying in practice. The deck also carries a DRDO scientist quote | Anonymised on the branch. The deck still needs the same fix | CEO | Fixed on branch
9 | Case Drone | Hero image | NEMI carbon-fibre defense UAS photograph | Customer property | High | A defence customer's airframe published without written consent | Get consent or replace the image | CEO | Not fixed
10 | Case Studies, BNC | Case 01 | BNC Motors presented as a client | Related party | High | Internal programme shown as third-party proof | Labelled as a NEMI subsidiary on the branch | CFO | Fixed on branch
11 | Case Studies, BNC | Case 01 | ~90% cost cut, $10M+ vs <$1M | Financial | High | The deck says under $0.5M. Site and deck contradict each other | Reconcile to one figure from the ledger | CFO | Fixed on branch
12 | Case Studies, BNC | Case 01 | 18 to 9 months, 100% spec met, sub-$1,000 price point | Performance | High | Needs the project plan, test report and BOM costing | Produce the evidence or remove | COO | Not fixed
13 | Case Studies, Coffee | Case 03 | 12+ to 5 weeks, >$200k to ~$100k, -20% BOM, 400 a month | Performance | High | Rests on the customer's own alternate quotes | Get written consent for that data or pull the figures | Sales + CFO | Partly fixed
14 | Case Studies, Drone | Case 04 | 16 to 4 months, $100k, 4/4 in-house, -20% BOM | Performance | High | Only partly in the deck | Evidence pack; the $500k benchmark and 5x claim already removed | CFO | Partly fixed
15 | Case Studies, PMI | Case 02 | 7 to 3 hrs, ~15 a day, 10-15 um, under a week to first supply | Performance | High | Machine logs and CMM records needed. The asterisk on '~15/day' has no footnote | Attach evidence, fix the orphan asterisk | COO | Partly fixed
16 | FAQ | Certification | Our factories are certified to AS9100D:2016 and ISO 9001:2015 | Certification scope | High | 'Our factories' is plural. Confirm every named site is inside the certificate scope | Check the certificates, name the covered entity | Quality | Not fixed
17 | Home | Hero | Trained inside our own factories. Proven on every part we ship. | Absolute | High | 'Every part' cannot be evidenced and reads as a technical guarantee | Soften to what the training logs support | CTO | Fixed on branch
18 | Home | Loop section | Our LMM runs all of them / every deployment compounds system intelligence | Absolute | High | Product capability stated as fact for all four stages | Already reworded on the branch: 'is built to run', 'designed to feed back' | CTO | Fixed on branch
19 | Home | Suite cards | Anvil LIVE, Orion LIVE, Atlas LIVE | Product status | High | The deck shows Phase 2 still in validation. This is the Momentus pattern | Badges removed on the branch. Reinstate only per the S-4 | CTO | Fixed on branch
20 | Home | Fortress Factories | sold as Manufacturing-as-a-Service, profitably, today | Financial | High | Consolidated financials show losses; deck says EBITDA-positive only by CY28E | Removed on the branch | CFO | Fixed on branch
21 | Home | Where Our Work Ends Up | F-35 fighter jet photograph | Implied customer | High | Placed under 'where our work ends up' it implies NEMI content in a fifth-generation fighter programme. Also a third-party image | Replace with our own hardware, or relabel the section as target markets | CEO + counsel | Partly fixed
22 | Home | Where Our Work Ends Up | Airliner, supercar, solar farm, ultrasound, camera drone, espresso machine | Implied customer | High | Same pattern: market imagery reads as work delivered | Relabel as markets we target, or use our own parts | CEO | Partly fixed
23 | Invest | Whole page | Coming soon. Our investment offerings are not open yet | Offering | High | The Aug 2026 deck sends investors to invest.nemilmm.com with a 30 Sep SAFE deadline | Decide: gated NDA portal, or remove the link from the deck | CEO + counsel | Not fixed
24 | Offerings | Stat | 9 category factories, one stack | Operational | High | Implies nine operating factories | Reworded, and the nine now carry the deck's own phase labels | COO | Fixed on branch
25 | About | Hero | More locations coming soon | Forward-looking | Medium | Expansion statement with no disclosure | Remove, or cover with the FLS note | Counsel | Fixed on branch
26 | About | India finance | Subramanian Ramaswamy titled Chief Financial Officer, India | Officer title | Medium | Two CFOs confuse the S-4 officer list | Retitled Finance Head on the branch | Counsel | Fixed on branch
27 | About | Eras timeline | 1913, 1950, 1980 archive photographs | Licensing | Medium | Third-party historical images with no credit | Confirm licences or replace with public-domain sources | Marketing | Not fixed
28 | About | Image | about-physical-ai.jpg robot arm | Stock imagery | Medium | Reads as our automation; appears to be stock | Confirm the licence or swap to our own robotics | Marketing | Fixed on branch
29 | All pages | Footer | (c) 2026 NEMI LMM | Entity name | Medium | Three names in play: NEMI LMM, Nemi Corp on the new CFO's profile, US HoldCo in the deck | Use the legal entity the S-4 will name | Counsel | Not fixed
30 | Careers | Hero | AI is going to transform manufacturing. We are leading the way. | Market position | Medium | Leadership claim with no basis | Soften to ambition | Counsel | Fixed on branch
31 | Careers | Hero | Proven daily in our own factories, on parts that ship | Technical | Medium | Same absolute as the home page | Align with whatever the home page settles on | CTO | Fixed on branch
32 | Case Studies | Page framing | Proof, not promises / delivered, not promised | Framing | Medium | Raises the evidentiary bar for every number below it | Keep only if every figure is documented | Marketing | Fixed on branch
33 | FAQ | Speedshop | Delivered first supply in under a week | Performance | Medium | Single instance stated as capability | Evidence, or reword as 'has delivered, once' | COO | Fixed on branch
34 | Home | Suite cards | Screenshots of Anvil, Orion, Atlas interfaces | Product evidence | Medium | Screens imply shipped software; must match what customers actually use | Confirm each screenshot is the real product, not a mock | CTO | Not fixed
35 | Home | Where Our Work Ends Up | BOSS E-TWIN electric motorcycle | Related party | Medium | A group brand shown alongside third-party markets without a label | Label as an internal programme like BNC | CFO | Not fixed
36 | Home, FAQ, Contact, Offerings | Service promise | 24 hrs / 24-48h / 48 hours / one business day, in four places | Inconsistency | Medium | Four different quote turnarounds on one site invites a complaint and looks careless in diligence | Pick one and use it everywhere | Sales | Fixed on branch
37 | LMM Stack | Images | stock-factory.jpg and stock-data.jpg | Stock imagery | Medium | Filenames say stock. Presented as the NEMI stack in context | Replace with our own floor and our own screens | Marketing | Fixed on branch
38 | LMM Stack | Body | Every unit shipped is another training run | Absolute | Medium | Same 'every' problem as the home page | Soften | CTO | Fixed on branch
39 | Offerings | Speed | Committed date on the quote, and the date treated as the contract | Contractual | Medium | A public contractual promise | Check the standard terms back it, or soften | Counsel | Fixed on branch
40 | Offerings | Tooling | 2x faster to first shot | Comparative | Medium | Benchmark not sourced | Produce the benchmark or drop the multiple | COO | Fixed on branch
41 | Offerings | Electronics | up to MIL-STD-810 / 461 grade | Technical | Medium | Qualification claim on regulated standards | Hold the test reports | Quality | Fixed on branch
42 | Offerings, Home | Videos | 14 factory and process videos | Licensing | Medium | Any stock footage needs a licence on file; own footage needs consent from people filmed | Inventory each clip and record its source | Marketing | Not fixed
43 | About | Team photos | Six factory photographs with empty alt text | Accessibility | Low | Screen readers announce nothing | Write alt text | Marketing | Fixed on branch
44 | Home | Data claim | Hardware has no internet to scrape | Technical | Low | Deck says 'no large public datasets'; the site overstates | Matched to the deck on the branch | CTO | Fixed on branch

## Next-level changes
Next-level changes: what the list does not cover yet
Checked 5 Oct 2026 against the website plan (18 Sep), vPresent (Oct 2026), the BCA-Ready branch and the live branch. Only items not already in the 44, or where an item's status is wrong.
# | Page | Where | What is there now | What to do | Why it matters | Links to # | Owner | Status
1 | Live site | About CEO bio · About, Home, Master Plan | "Built NEMI greenfield to 300k sq ft" and "…Manufacturing-as-a-Service, profitably, today" are back on main, the branch nemilmm.com is pulled from (the 1 Oct About rebuild brought them back) | Bring the branch fixes to main before the next pull to the server | #1 and #20 read "Fixed on branch", but the live site still says both | 1, 5, 20 | CEO | Not fixed
2 | vPresent deck | Slide 21, CEO bio | "built NEMI greenfield to 300k sq ft" | "Acquired and expanded NEMI's manufacturing base to over 300,000 sq ft in India", same as the site | The deck contradicts itself: slide 17 says the MaaS core was acquired two years ago | 1 | CEO | Not fixed
3 | Case Studies, BNC | Case 01 | Site: "<$1M program cost". vPresent: "under $0.5M · 2× faster · 10× cheaper" | Take the ledger figure and use it on both | #11 reads "Fixed on branch", but site and deck still differ | 11 | CFO | Not fixed
4 | Case Drone | Meta text, summary, results table | "…16 months and ." · "(vs 16 months / )" · empty benchmark cell | "Delivered in 4 months against a 16-month benchmark." Remove the empty cell | Broken sentences left when the $500k benchmark came out | 14 | Marketing | Broken on branch
5 | FAQ, Contact | Locations | "…Chennai and Coimbatore, India, ." · empty "coming soon" line | "…Chennai and Coimbatore, India." Delete the empty line | Broken sentences left when "more locations coming" came out | 25 | Marketing | Broken on branch
6 | Case Studies, Coffee | Results table | "Benchmark withheld" | Remove the benchmark row and show only NEMI's own figure | "Withheld" reads as hiding something | 13 | Sales + CFO | Not fixed
7 | About, Offerings | Hero, Tooling, SPMs, Motors | "proven every day in our own full-stack factories" · "Proven across automotive and aerospace customers" · "proven at rate" · "dyno-proven" | "run every day" · "in use with automotive and aerospace customers" · "tested at rate" · "dyno-tested" | Same word #17 and #31 took out elsewhere; four are left | 17, 31 | CTO | Not fixed
8 | About | India leadership | Branch: "Business Unit Leader" ×3, "Finance Head · India", "Ramaswamy" | vPresent says "President" ×3, "CFO · India", "Ramasamy". Pick one set and match the S-4 word for word | Site and the Oct deck now disagree on titles and spelling | 26 | CEO + counsel | Not fixed
9 | About | Advisory bench | Branch: "Dr. Sampath Ravinarayanan · Chairman · AxisCades" · Naoya "Board Advisor" | vPresent: "Dr. Sampath Ravi Narayanan · Board Advisor · Chairman & MD, AXISCADES" · Naoya "CEO, Musashi Auto Parts India". Match one source | Name spelling and titles differ from the deck | 3 | CEO + counsel | Not fixed
10 | All pages | Footer | © 2026 NEMI LMM | vPresent names the entity: NEMI CORP, US HoldCo (Texas), redomiciled Sept 2026. Counsel confirms the exact form | Gives #29 its likely answer | 29 | Counsel | Not fixed
11 | This list | Reference deck | The list was checked against the Aug vShare deck | Re-check against vPresent (Oct). It moves #20 (EBITDA+ now CY27E, not CY28E) and #23 (investors now go to invest@nemilmm.com, closes Oct–Dec) | The newer deck changes two answers | 20, 23 | Marketing | Not fixed
12 | Whole site | All pages | — | Take the deck's tone, not its numbers. Keep off: ARR, 40+ customers, 90%+ retention, LTV/CAC, ~9× productivity, TAMs, projections, SPAC / LOI / timeline, valuation | Plan: no number that is not in a filed document; vPresent is a private SAFE deck under NDA |  | Marketing | Rule

## Light changes
Light changes: wording to match the vPresent voice
Low risk, quick edits. Each one brings a line closer to how the October deck says it.
# | Page | Where | What is there now | Change it to | Why
1 | Home | Hero | "Not AI for manufacturing, AI that runs our manufacturing." | "Not AI for manufacturing — AI that runs manufacturing, winning on cost, quality and speed." | vPresent slide 6
2 | Careers | Hero | "We intend to be part of it." | "NEMI is building the infrastructure for this shift." | vPresent slide 4: confident, no claim
3 | Case Studies, BNC | Case 01 label | "Internal program · NEMI LMM × BNC Motors (NEMI subsidiary)" | "Test-bed EV · BNC Motors, our subsidiary" | vPresent slide 11: same disclosure, shorter
4 | Master Plan | Letter | "Fortress Factories in India — over 300,000 sq ft in India" | Say "in India" once | Repeated words
5 | Case Studies, Drone, FAQ | Body | "programme" and "program" both used | "program" everywhere | US entity, US readers; the deck uses US spelling
6 | Home | Contact block | "We'll revert within 24 to 48 hours." | "We'll reply within 24 to 48 hours." | "Revert" reads oddly to US readers
7 | LMM Stack, About | Factory footprint | "300,000+ sq ft in India" | Add the deck's note: "Present footprint · expansion planned" | vPresent slide 10 footnote; replaces "more locations coming soon"
8 | About, Master Plan | Phases | "Automate the Easy Part First: eNvision + Engineer" | "Phase 1 · Automate design" · "Phase 2 · Automate the factory" · "Phase 3 · Open the platform" | vPresent slide 13: one story everywhere
9 | Home | Suite cards | "Live" badges removed | Caption: "Screens from our working software" | vPresent slide 7 says "live screens, not mockups"; a caption keeps that without a status badge
10 | Whole site | Voice | "every", "only", "compounds" | Say what is designed, targeted or on the roadmap. Use "~" for approximations, mark actual vs target | vPresent labels every figure (actual, E, forecast, target)